## C. ERP Design
RACI-matrix legend:
| Initiative C. ERP Design work plan | [16 empty] | R - responsible |  |  |  |  | C - consult | [6 empty] | Development |  |  |  | Approval
| Draft version. The final version will be based on the diagnostic results. | [16 empty] | A - accountable |  |  |  |  | I - informed
|  | RACI-matrix | [6 empty] | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  | M7
# | ACTIVITIES | KPMG | PMO | FIN | HR | PROC | DATA | IT | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | DELIVERABLES
1 | Current state assessment and business requirements definition
1.1 | Collection of inventory of information systems and automation tools for centralized functions (Procurement, Warehouse Management, Inventory Management, Human Resource Management, Accounting and Reporting), and their current business process flows (prepared by BIR Ecosystem Functions) | C | R | C | C | C |  | A | [28 empty] | Inventory of information systems and automation tools
1.2 | Interview with centralized functions (Procurement, Warehouse Management, Inventory Management, Human Resource Management, Accounting and Reporting) to understand their current processes (both centralized and not centralized) and limitations/dependencies, identify initial business requirements for target state | R | C | A | A | A | C | A | [28 empty] | - Interview schedule - Meeting minutes - Business requirements catalog format
1.3 | Preparation of complete list of business requirements by functional experts | C | A | R | R | R | C | R | [28 empty] | Catalog of business requirements
1.4 | Agree on prelimiary target ERP platform to align on target vision of centralized functions | R | C | A | A | A |  | A
1.5 | Facilitation sessions by KPMG with centralized functions to help them to design target business process flows (3-4th level) based on: - Regulatory documents and legislation for financial sector (by Central Bank) where applicable - Analysis of existing process maps and flows, policies, procedures, current automation, usage of AI in process | R | C | A | A | A |  | A | [28 empty] | Presentation on business processes design formats and approach
1.6 | Design of target business process flows by functional experts of BIR Ecosystem (supported by KPMG facilitation meetings when relevant) | C | A | R | R | R |  | C | [28 empty] | Draft target business processes
1.7 | Enrichment of target business processes (within ERP scope) by KPMG based on: - results of activity 1.5 - apllication of reference processes and functional capability maps/blueprints available for KPMG from similar projects and best practices - Available capabilities of selected 1-2 popular ERP solutions for considerations. | R | A | C | C | C | C | C | [28 empty] | Draft target business processes
1.8 | Validation session with functional leaders to confirm target business processes and business requirements | R | C | A | A | A | C | A | [28 empty] | Finalized target business processes Finalized business requirements
| Milestone: business requirements for ERP are validated |  | A
2 | Target ERP architecture design
2.1 | Design 2-3 scenarios for target ERP vision (ERP-only for all selected centralized perimeter, or ERP + other tailored solutions/automation options, or lighter tools, etc.) with achievable benefits, pros/cons and preliminary investment amount | R | C | C | C | C | C | C | [28 empty] | Target ERP scenarios/options
2.2 | Validation session with Project Leader and Functional leaders facilitated by KPMG to agree on target scenario/option | C | A | A | A | A | C | A | [28 empty] | Target ERP scenarios/options
2.3 | Design the target architecture for ERP (and automation ecosystem around ERP) for selected scenario | R | I | C | C | C | C | C | [28 empty] | Target ERP architecture
2.4 | Prepare requirements on master data for ERP, reporting types/formats, ecosystem-level system integration model through common process & data standards. | R | I | C | C | C | A, C | A, C | [28 empty] | Target ERP architecture
| Milestone: target ERP scenario/option and architecture validated |  | A
3 | ERP requirements package
3.1 | Based on all inputs from business requirements and target ERP architecture, develop RFI and detailed Request for Proposal (RFP) which includes functional, technical, integration, master data, non-functional requirements for the ERP landscape | R | A | C | C | C | C | C | [28 empty] | Draft ERP requirements package
3.2 | Jointly select potential system integrators to share RFI | C | A | I | I | I | I | C | [28 empty] | List of potential system integrators
3.3 | Pre-tender communications to validate RFP and capabilties of market vendors - advisory support by KPMG during communication with potential vendors and system integrators to ensure that RFP requirements and client expectations are clear and can be implemented | C | A | C | C | C | C | C
3.4 | Finalize ERP requirements package ready for further tender process | R | A | C | C | C | C | C | [28 empty] | ERP requirements package
| Milestone: target ERP requirements package validated |  | A
4 | Implementation roadmap
4.1 | Develop detailed action plan for the implementation of ERP, which includes for each key activity – decomposition of the activity into steps and components, work results of the activity, responsible parties/persons, timeline, milestones, success criteria/acceptance criteria, related risks, dependency between activities, etc. | R | A | C | C | C | C | C | [28 empty] | ERP implementation roadmap
4.2 | Present initiative results to the key stakeholders | R | A | I | I | I | I | I | [28 empty] | Presentation on project results
| Milestone: target ERP implementation roadmap validated |  | A
| Minumum allocated FTE | 5 | 1 | 1 | 1 | 1 | 0.2 | 1

## HRM Target Vision
Core HRM — Target Operating Model
Initiative C · ERP Design ¦ HRIS workstream ¦ One multi-tenant HR core for BIR Ecosystem verticals; adjacent talent capabilities integrated or delivered as ERP modules (TBD).
Design Principles
Single source of truth | Employee, position and organization data mastered once and distributed outward.
Configurable, not coded | Fields, forms, workflows, checklists and document templates defined by HR admins without vendor development.
Open by design | API-first architecture and an open reporting data model for analytics and ecosystem integration.
Compliant & auditable | Full e-signature document lifecycle, immutable audit trail, AZ labour-law compliance built in.
Capability Architecture
HR-OWNED CORE
Organization & Headcount | HRIS Core & Master Data | HR Operations & Lifecycle | Documents & Certificates
Labour Relations & Orders | Pre-Payroll | Benefit Management | Job Architecture & Grading
PLATFORM (cross-cutting)
Self-Service Portal | Workflow & Checklist Engine | E-Signature & Document Flow | Open Data & Reporting
Security & Audit (RBAC) | Configurability & Multi-tenancy
INTEGRATED / TBD
Recruitment (Hiring Portal) | Learning (iSpring / ERP LMS) | Performance (SAP / ERP) | KPI Engine
Active Directory | "360" Intranet | Internet Banking | EMAS / EGOV / Finance
Multi-Tenant Scope
Central Office | BIR Ecosystem — shared standards & governance
Birbank | HRB, ELMA, SAP Performance, iSpring, 360, Jira, Hiring Portal, Excel
Pashapay | 1C, Jira
Birmarket | 1C

## HRM Requirements (1.3)
HRM Catalog of Business Requirements
Initiative C · ERP Design ¦ Activity 1.3 deliverable (HR = Responsible) ¦ Catalog of HR business requirements for the target ERP/HRIS. Scope: HR-owned Core HRM across BIR Ecosystem verticals (Birbank, Pashapay, Birmarket). MoSCoW prioritisation.
ID | Module | Capability | Requirement | Type | Priority
A. HRIS CORE & MASTER DATA
HR-01 | HRIS Core | Employee Master Data | Single, version-controlled source of truth for personal, contractual, job, position and grade data with effective-dating. | Functional | Must
HR-02 | HRIS Core | Employment Types | Register and manage both employment-contract staff and service-contract (civil) workers under one model with distinct rule sets. | Functional | Must
HR-03 | HRIS Core | Multi-tenancy | Verticals (Birbank, Pashapay, Birmarket) as discrete tenants/legal entities under one platform; shared standards, segregated data and configuration. | Functional | Must
HR-04 | HRIS Core | Configurability | Business-admin definition of new fields, forms, workflows, checklists and validation rules without vendor code changes. | Non-functional | Must
HR-05 | HRIS Core | Open Data Architecture | Open, documented data model exposing reporting/BI access via views, API and export. | Non-functional | Must
HR-06 | HRIS Core | Bulk Operations | Validated bulk import/update with templating and error handling for mass changes and initial load. | Functional | Must
HR-07 | HRIS Core | Data Migration | Structured migration from legacy systems (HRB, 1C, Excel) with mapping, validation, reconciliation and retained history. | Non-functional | Must
HR-08 | HRIS Core | Data Privacy | Personal-data protection: consent, retention, right-to-erasure, per-tenant residency. | Non-functional | Must
B. ORGANIZATION, JOB ARCHITECTURE & HEADCOUNT
HR-09 | Organization | Dual Structure | Manage traditional (Office, Department, Section, Division, Team) and agile (Expertise Centre, Tribe, Chapter, Squad) structures in parallel. | Functional | Must
HR-10 | Organization | De Jure / De Facto | Maintain separated legal (De Jure) and actual-reporting (De Facto) hierarchies plus matrix/dotted-line. | Functional | Must
HR-11 | Organization | Establishment Control | Manage approved establishment (positions, FTE, vacancy) vs actual headcount; effective-dated and versioned. | Functional | Must
HR-12 | Job Architecture | Job Catalogue | Job catalogue: job families, profiles and standardised job codes shared across tenants. | Functional | Must
HR-13 | Job Architecture | Grading | Grading module: grade structures, mapping of jobs to grades, grade-driven eligibility. | Functional | Must
HR-14 | Job Architecture | Job Descriptions | Job-description management with full version history and approval workflow. | Functional | Must
C. HR OPERATIONS & EMPLOYEE LIFECYCLE
HR-15 | HR Operations | Self-Service Portal | Full employee-lifecycle self-service (requests, approvals, documents, status) for employees and managers across web and mobile. | Functional | Must
HR-16 | HR Operations | Hire & Onboard | End-to-end hiring and onboarding with system-driven checklists and cross-function task assignment. | Functional | Must
HR-17 | HR Operations | Transfers & Promotions | Manage transfers, promotions, rotation, acting and temporary assignments, effective-dated. | Functional | Must
HR-18 | HR Operations | Leave Management | Leave by type (annual, additional, hazard, maternity, social, unpaid, education) with accrual rules, balances and planning. | Functional | Must
HR-19 | HR Operations | Business Travel | Business-travel requests, approval, duration and hand-off to pre-payroll and benefits. | Functional | Must
HR-20 | HR Operations | Overtime & Absence | Capture and approve overtime, sickness and absence; feed time and payroll inputs. | Functional | Must
HR-21 | HR Operations | Probation & Contract Term | Track probation and contract-term expiry with automated alerts and decision workflow. | Functional | Must
HR-22 | HR Operations | Resignation & Offboard | Manage resignation and termination, clearance, archiving and downstream deprovisioning. | Functional | Must
D. EMPLOYEE DOCUMENTS, REFERENCES & CERTIFICATES
HR-23 | Documents | Reference Letters | Generate reference / employment-verification letters (proof of employment) on demand via self-service, with templates and e-signature. | Functional | Must
HR-24 | Documents | Salary Certificates | Generate salary / income certificates and statements (e.g. for banks, embassies) with controlled data and signature. | Functional | Must
HR-25 | Documents | Embassy / Travel Letters | Generate letters for embassy, visa and travel purposes from validated employee data. | Functional | Should
HR-26 | Documents | Document Requests | Self-service request, approval, generation and delivery of any HR document with status tracking. | Functional | Must
HR-27 | Documents | Document Lifecycle | Full document circulation, versioning and archive managed directly in HRIS — no external document system. | Functional | Must
HR-28 | Documents | E-Signature | Native signing via e-signature, Asan Imza and SIMA, with register, numbering and audit. | Functional | Must
E. LABOUR RELATIONS & ORDERS
HR-29 | Labour Relations | Order Management | Generate and manage all HR order types (appointment, termination, change, acting, leave, deduction, travel, bonus, disciplinary). | Functional | Must
HR-30 | Labour Relations | Smart Checklists | System-generated checklist per order type, e.g. director appointment prompts management-board protocol, regulator notification and interview-panel minutes. | Functional | Must
HR-31 | Labour Relations | Templates | Configurable, legally-compliant order and document templates. | Functional | Must
HR-32 | Labour Relations | Statutory Reporting | Native statutory HR reporting per AZ legislation. | Functional | Must
HR-33 | Labour Relations | Compliance & Archive | Labour-law compliant records, registers and archiving per local legislation. | Non-functional | Must
F. PRE-PAYROLL
HR-34 | Pre-Payroll | Time & Attendance | Capture time and attendance across work regimes (standard, 5-day, 6-day, shift). | Functional | Must
HR-35 | Pre-Payroll | Aggregated Accounting | Aggregated time accounting on monthly, quarterly and annual bases. | Functional | Must
HR-36 | Pre-Payroll | Payroll Inputs | Consolidate approved time, leave, overtime and travel into validated payroll inputs with retroactive recalculation. | Functional | Must
HR-37 | Pre-Payroll | Period Close | Month-end close controls: cross-checks, validations and sign-off. | Functional | Should
G. BENEFIT MANAGEMENT
HR-38 | Benefits | Allowances | Administer allowances (rental, meal, travel and role-based benefits) by eligibility rules. | Functional | Must
HR-39 | Benefits | Eligibility | Configure benefit plans and eligibility by grade, position and tenant. | Functional | Should
HR-40 | Benefits | Card & Banking | Order salary cards and manage payroll-banking instructions via internet-banking integration. | Integration | Must
H. KPI, PERFORMANCE & TALENT
HR-41 | KPI | KPI Engine | KPI calculation module supporting monthly, quarterly and annual KPIs. | Functional | Must
HR-42 | KPI | Annual Source | Annual KPI derived from performance-evaluation results (SAP Performance or ERP module — TBD). | Integration | Must
HR-43 | Performance | Evaluation | Performance and 360 evaluation — integrate SAP Performance or deliver ERP module (TBD). | Integration | Must
HR-44 | Learning | LMS | Integrate employee list and structure into iSpring, or deliver an ERP LMS module (TBD). | Integration | Must
HR-45 | Recruitment | Hiring Portal | Integrate existing hiring portal; convert candidate to employee record without re-keying. | Integration | Must
I. INTEGRATION & ECOSYSTEM
HR-46 | Integration | Active Directory | HRIS as source of truth; provision and sync identity and attributes to Active Directory. | Integration | Must
HR-47 | Integration | "360" Intranet | Publish structure and employee data to the internal intranet platform. | Integration | Must
HR-48 | Integration | Internet Banking | Integrate with internet banking for salary-card issuance and payment instructions. | Integration | Must
HR-49 | Integration | EMAS | Integrate with EMAS for statutory / administrative HR processing (bi-directional). | Integration | Must
HR-50 | Integration | EGOV | Integrate with government e-services for statutory submissions. | Integration | Must
HR-51 | Integration | Finance / Payroll | Provide payroll inputs and cost/headcount data to Finance (FIN-owned engine). | Integration | Must
HR-52 | Integration | Open API | API-first architecture open to all internal and external integrations. | Non-functional | Must
HR-53 | Integration | Reporting | Standard and ad-hoc HR analytics delivered to the ecosystem reporting layer. | Functional | Must
HR-54 | Integration | Legacy Retirement | Absorb all legacy HR processes into HRIS to enable retirement of ELMA, HRB and Excel tooling. | Non-functional | Must

## HRM Processes (1.6)
HRM Target Business Processes
Initiative C · ERP Design ¦ Activity 1.6 deliverable (HR = Responsible) ¦ Sample target process flows (Level 3-4). All execution within HRIS via self-service, workflow, smart checklists and native e-signature.
Process | Step | Activity | Actor | System Capability | Output
Leave Management | 1 | Employee submits leave request (type, dates) via self-service portal | Employee | Self-service | Leave request
Leave Management | 2 | System validates entitlement, balance and accrual rules by leave type | System | Leave management | Validated balance
Leave Management | 3 | Request routed for multi-level approval (manager, HR) | Manager / HR | Workflow | Approval
Leave Management | 4 | Leave order generated and signed (e-signature / Asan Imza / SIMA) | HR | Orders + e-sign | Signed order
Leave Management | 5 | Balance updated; absence recorded; input released to pre-payroll | System | Pre-payroll | Updated balance
Business Trip | 1 | Employee submits business-trip request (destination, dates, purpose) | Employee | Self-service | Trip request
Business Trip | 2 | System checks policy, budget and approval matrix | System | Workflow | Policy check
Business Trip | 3 | Multi-level approval (manager, budget owner, HR) | Manager / HR | Workflow | Approval
Business Trip | 4 | Business-trip order generated and signed; travel/allowance computed | HR | Orders + benefits | Signed order
Business Trip | 5 | Hand-off to pre-payroll and benefits; trip recorded; reconciliation on return | System | Pre-payroll / benefits | Payroll input
Resignation | 1 | Employee submits resignation request via self-service | Employee | Self-service | Resignation request
Resignation | 2 | Manager and HR acknowledge; notice period and last working day calculated | Manager / HR | Workflow | Confirmed dates
Resignation | 3 | Offboarding checklist triggered (clearance, assets, knowledge handover) | HR / System | Checklist engine | Clearance status
Resignation | 4 | Termination order generated and signed; final settlement input prepared | HR | Orders + e-sign | Signed order
Resignation | 5 | Deprovision AD / 360 / banking; archive record; statutory reporting | System | Integration + archive | Closed record
Three representative flows shown. Same pattern (self-service request → validation → approval → signed order → downstream update) applies to hire, transfer, overtime, document requests and other lifecycle events.

## HR System Inventory (1.1)
HR System & Tool Inventory — by Vertical
Initiative C · ERP Design ¦ Activity 1.1 input (HR scope) ¦ HR systems across BIR Ecosystem verticals, their function and target disposition. Target HRIS consolidates the HR core into one multi-tenant platform.
# | Vertical | System / Tool | Primary HR Function | Target Disposition | Priority
BIR Ecosystem — Central Office
1 | Central | Target HRIS / HRM (new) | Unified multi-tenant core HR platform | Consolidate | Must
Birbank
2 | Birbank | HRB | Core HR system of record (legacy) | Migrate | Must
3 | Birbank | ELMA | Document flow & process automation (BPM) | Retire | Must
4 | Birbank | SAP Performance | Performance & 360 evaluation | Integrate | Must
5 | Birbank | iSpring LMS | Learning management | Integrate | Must
6 | Birbank | 360 Intranet | Internal employee portal | Integrate | Must
7 | Birbank | Jira | HR ticketing & task tracking | Replace | Should
8 | Birbank | Hiring Portal | Recruitment front-end | Integrate | Must
9 | Birbank | Excel databases | Manual records, KPI & ad-hoc tracking | Replace | Must
Pashapay
10 | Pashapay | 1C | Core HR / accounting-linked HR records | Migrate | Must
11 | Pashapay | Jira | HR ticketing & task tracking | Replace | Should
Birmarket
12 | Birmarket | 1C | Core HR / accounting-linked HR records | Migrate | Must
Multi-tenancy: HRB (Birbank), 1C (Pashapay, Birmarket) and Excel HR records consolidate into one multi-tenant HRIS. HRB is Birbank-only and not used by subsidiaries.

## Integration & Migration
Integration & Legacy Migration Strategy
Initiative C · ERP Design ¦ HR perspective ¦ Consolidate the HR core across verticals into one multi-tenant HRIS; integrate the ecosystem; retire legacy document & BPM tooling.
System / Platform | Vertical | Current Role | Target Disposition | Direction | Priority | Design Note
Target HRIS (new) | Central | Unified multi-tenant HR core | Build | - | Must | One platform; shared standards, segregated tenant data
HRB | Birbank | Core HR system of record | Migrate | Source | Must | Full migration with history; then retire
1C (HR) | Pashapay / Birmarket | Core HR records | Migrate | Source | Must | Migrate HR data into HRIS
ELMA | Birbank | Document flow & BPM | Retire | - | Must | Flows rebuilt natively in HRIS; decommission
Jira | Birbank / Pashapay | HR ticketing | Replace | - | Should | Absorbed by self-service & workflow
Excel databases | Birbank | Manual records & KPI | Replace | - | Must | Replaced by HRIS core & KPI engine
SAP Performance | Birbank | Performance & 360 evaluation | Integrate | Bi-directional | Must | Send structure; pull annual evaluation for KPI
iSpring LMS | Birbank | Learning management | Integrate | Outbound | Must | Send employee list & structure
360 Intranet | Birbank | Internal employee portal | Integrate | Outbound | Must | Publish structure & employees
Hiring Portal | Birbank | Recruitment front-end | Integrate | Inbound | Must | Candidate to employee, no re-keying
Active Directory | Group | Identity & accounts | Integrate | Outbound | Must | HRIS is source of truth; provision to AD
Internet Banking | Group | Salary cards & payments | Integrate | Outbound | Must | Card issuance & payment instructions
EMAS | Group | Statutory / administrative HR | Integrate | Bi-directional | Must | Interface maintained; not migrated
EGOV | Group | Government e-services | Integrate | Bi-directional | Must | Statutory submissions
E-sign / Asan Imza / SIMA | Group | Document signing | Integrate | Bi-directional | Must | Native signing across document lifecycle
Finance / Payroll | Group | Payroll engine (FIN-owned) | Integrate | Outbound | Must | Pre-payroll inputs provided; engine not HR-owned

## HR Master Data (2.4)
HR Master Data Requirements
Initiative C · ERP Design ¦ Activity 2.4 input ¦ Core HR master-data objects, attributes, code standards and ownership. Basis for the ERP master-data model and reporting.
Master Data Object | Key Attributes | Code / Standard | Owner | Notes
Employee | Person ID, name, demographics, contact, status, employment type (labour / service contract) | Unique employee ID | HR | Single source of truth; effective-dated
Employment / Contract | Contract type, start/end, probation, FTE, working-time regime | Contract number | HR | Supports employment- and service-contract staff
Position | Position ID, title, reporting line, vacancy, establishment flag | Position code | HR | Establishment vs actual headcount
Job | Job profile, job family, job description (versioned) | Job code | HR | From Job Catalogue module
Grade | Grade level, salary band linkage, eligibility rules | Grade code | HR | From Grading module
Organization Unit | Unit name, type, parent, validity, structure type | Org unit code | HR | Traditional & agile; De Jure / De Facto
Tenant / Legal Entity | Vertical, legal entity, country | Tenant code | HR | Birbank / Pashapay / Birmarket
Cost Centre | Cost centre code, mapping to org unit | Cost centre code | Finance | HR consumes; owned by Finance
Location | Site, address, region | Location code | HR / Admin | Multi-tenant scoping
Leave Type | Type, accrual rule, paid/unpaid, statutory basis | Leave type code | HR | Annual, additional, hazard, maternity, social
Allowance / Benefit | Type, eligibility, value basis | Benefit code | HR | Rental, meal, travel, role-based
Order Type | Order category, template, required checklist | Order type code | HR | Drives smart-checklist engine
Document Type | Reference / salary / embassy letter, template, signature, retention | Document type code | HR | E-signature / Asan Imza / SIMA